## Screening Matrix
Project Screening Matrix
PROJECT NAME: XXXXXXXXX
A. Primary Considerations |  |  | Part A Weighting: | 40
Weighting Guidelines
| Consideration | Rating | Weighting | Weighted Value | Low | Medium | High
| Time constraints for project delivery | Medium | 35 | 21 | Sufficient time for standard procurement | Need to accelerate project delivery | Insufficient time for standard delivery
| Status of environmental approvals | Medium | 25 | 15 | Not started | Underway | Complete
| Availability of funding | Low | 25 | 5 | Unknown | Multiple funding periods/sources | Funding in place and available
| Well defined scope | Medium | 15 | 9 | Concept only | Scope needs refinement | Clearly defined scope
| Total |  | 100 | 50
|  |  | Weighted Total: | 20
B. Secondary Considerations |  |  | Part B Weighting: | 35
Weighting Guidelines
| Consideration | Rating | Weighting | Weighted Value | Low | Medium | High
| Overall project complexity | High | 10 | 10 | Simple project | Moderate complexity | Significant complexity
| Complexity of performance requirements | High | 10 | 10 | Performance requirements unknown | Performance requirements established | Performance requirements known
| Project size | High | 10 | 10 | < $ 1 million | $1 to $ 5 million | > $5 million
| Availability of qualified teams | Medium | 10 | 6 | < 3 possible bidders | 3 to 5 possible bidders | > 5 bidders
| Owner experience and resources | Medium | 10 | 6 | First design/build project | Some experience | Significant experience
| Cost of project | Medium | 10 | 6 | No fixed budget | Some budget flexibility | Fixed budget
| Degree of team collaboration | High | 10 | 10 | Unknown teaming arrangements | May know some team members | Owner familiar with the teams
| Number of contracts | High | 10 | 10 | Many separate small contracts | Several contracts but manageable | One overall contract
| Allocation of risks | Medium | 10 | 6 | Owner retains majority of risk | Risks shared between owner and D/B team | Transfer majority of risk to D/B team
| Interest in innovation | High | 10 | 10 | Low | Medium | High
| Total |  | 100 | 84
|  |  | Weighted Total: | 29.4
C. Other Considerations |  |  | Part C Weighting: | 25
Weighting Guidelines
| Consideration | Rating | Weighting | Weighted Value | Low | Medium | High
| Data Security | Medium | 20 | 12 | Low data security criteria | Organization requires certain level of security | Data that should be kept safe of with security protocols
| Operational constraints | High | 5 | 5 | Significant operational constraints | Some operational constraints | No operational constraints
| Utility relocations | Low | 10 | 2 | Significant utility relocations | Some utility relocations | Minimal utility relocations
| QC/QA responsibilities | High | 30 | 30 | Owner's responsibility | Shared responsibility | Design/build entity responsibility
| Performance guarantees/warranties | Medium | 10 | 6 | Short term coverage | Medium term coverage | Long term warranties
| Design reviews/approvals | High | 5 | 5 | Significant design review required | Moderate owner review required | Short turn around/minimal review
| Legal frame or requirements | Low | 10 | 2 | No legal frame require | Legal advisory desired | Legal workframe has to be established
| Ownership of intellectual property | Low | 10 | 2 | Significant intellectual property | Some intellectual property | No intellectual property
| Total |  | 100 | 64
|  |  | Weighted Total: | 16
Sub Totals |  |  |  |  | Decision Range
| A. Primary Considerations |  | 40 | 20 | From | To | D/B Applicability
| B. Secondary Considerations |  | 35 | 29.4 | 0 | 50 | No
| C. Other Considerations |  | 25 | 16 | 50.01 | 64.99 | Can Consider
| Grand Total |  | 100 | 65.4 | 65 | 100 | Yes
| Decision |  |  | Yes
Note on E7: Octavio Gutierrez Barreto: Valores de ejemplo
Note on E35: Octavio Gutierrez Barreto: Valores agregados como ejemplo
Note on B64: Octavio Gutierrez Barreto: Quality Assurance and Control
Note on D80: Gutierrez, Octavio (LatAm): No debe rebasar el 100%, y siempre tiene que dar 100%